## Schedule
Project Start Date: | 2024-01-16 | [5 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08
Project Name | Communications System Program | time axis 2024-01-15 to 2024-07-14
 | time axis 2024-01-15 to 2024-07-14
Activity | Assinged To | Start | End | Days | Status | %Done
Requirements
Project.init() Meeting | ALL | 2024-01-31 | 2024-01-31 |  | Complete | 100% | bar: 2024-01-31
Project.init() Presentation | ALL | 2024-02-01 | 2024-02-01 | 1 | Complete | 100% | bar: 2024-02-01
SRS Meeting | ALL | 2024-02-11 | 2024-02-11 | 0 | Complete | 100% | bar: 2024-02-11
List all requirements/use cases | ALL | 2024-02-11 | 2024-02-18 | 5 | Complete | 100% | bar: 2024-02-18
Use Case Diagram | CS | 2024-02-11 | 2024-02-28 |  | Complete | 100% | bar: 2024-02-28
Initial Class Diagram | JM | 2024-02-11 | 2024-02-28 |  | Complete | 100% | bar: 2024-02-28
Sequence Diagrams | HA, JG, LM | 2024-02-11 | 2024-02-28 | 13 | Complete | 100% | bar: 2024-02-28
SRS Presentation Meeting | ALL | 2024-02-28 | 2024-02-28 | 1 | Complete | 100% | bar: 2024-02-28
Requirements Presentation | ALL | 2024-02-29 | 2024-02-29 | 1 | Complete | 100% | bar: 2024-02-29
SRS Submital Due | ALL | 2024-02-29 | 2024-02-29 | 1 | Complete | 90% | bar: 2024-02-29
Design | [5 empty] | 0%
Initial Design Meeting | ALL | 2024-03-05 | 2024-03-05 | 1 | Complete | 100% | bar: 2024-03-05
Complete Initial Class Diagram | ALL | 2024-03-05 | 2024-03-12 |  | Complete | 100% | bar: 2024-03-12
Updated use cases | CS,HM | 2024-03-12 | 2024-03-24 |  | Complete | 100%
Updated Sequence Diagrams | JM,LM,JG | 2024-03-12 | 2024-03-24 |  | Complete | 100%
Updated SRS Meeting | ALL | 2024-03-24 | 2024-03-24 |  | Complete | 100%
Design Presentation Meeting | ALL | 2024-03-27 | 2024-03-27 |  | Complete | 100% | bar: 2024-03-27
Design Presentation | ALL | 2024-03-28 | 2024-03-28 |  | Complete | 100% | bar: 2024-03-28
Design Submital Due | ALL | 2024-03-28 | 2024-03-28 |  | Complete | 95% | bar: 2024-03-28
Implementation / Testing ?
GUI Mock-up | CS, JM, LM | 2024-03-29 | 2024-04-05 |  | Complete | 100% | bar: 2024-04-05
GUI/Server Implemenation Meeting | ALL | 2024-03-31 | 2024-03-31 |  | Complete | 100% | bar: 2024-03-31
Standard/IT GUI Implementation | CS, JM, LM | 2024-04-01 | 2024-04-12 |  | Complete | 100% | bar: 2024-04-12
Add/Modify User Panel | JM | 2024-04-07 | 2024-04-21 |  | Blocked | 80% | bar: 2024-04-21
Create New Chat Panel | JM | 2024-04-07 | 2024-04-21 |  | In Progress | 90%
Message Panel GUI Design Complete | LM | 2024-04-01 | 2024-04-21 |  | Complete | 100%
Message Panel Handlers | LM | 2024-04-07 | 2024-04-23 |  | Complete | 100%
Notificaitions on GUI | LM |  |  |  | SKIPPING | 10%
GUI Layout West/Center Panels | CS | 2024-04-01 | 2024-04-19 |  | Complete | 100%
Client to Server Communication | CS | 2024-04-01 | 2024-04-19 | 15 | Complete | 100% | bar: 2024-04-19
Messages Implementation | CS, JG, HM | 2024-04-01 | 2024-04-29 |  | In Progress | 85% | bar: 2024-04-29
Sever Implementation | JG, HM, CS | 2024-04-01 | 2024-04-12 |  | In Progress | 80% | bar: 2024-04-12
Database Implementation | HM, CS | 2024-04-14 | 2024-04-28 |  | Complete | 100%
Build User | HM, CS | 2024-04-14 | 2024-04-28 |  | Complete | 100%
Build Chat | CS | 2024-04-14 | 2024-04-28 |  | Complete | 100%
Appending to Files | LM | 2024-04-14 | 2024-04-28 |  | Complete | 100%
Client Handler Message Routing | JG | 2024-04-01 | 2024-04-26 |  | Blocked | 90%
"Put it all together" Meeting | ALL | 2024-04-21 | 2024-04-21 |  | Complete | 100% | bar: 2024-04-21
ServerMessage Testing | JG | 2024-04-15 | 2024-04-29 |  | Complete | 100% | bar: 2024-04-29
Finishing Steps | ALL | 2024-04-26 | 2024-04-26 |  | Complete | 100%
Review Meeting | ALL | 2024-04-28 | 2024-04-28 |  | Complete | 100% | bar: 2024-04-28
Final Presentation Meeting | ALL | 2024-04-29 | 2024-04-29 |  | Complete | 100% | bar: 2024-04-29
Final Presentation | ALL | 2024-04-30 | 2024-04-30 |  | Complete | 100% | bar: 2024-04-30
Final Submital Due | ALL | 2024-04-30 | 2024-04-30 |  | Complete | 100% | bar: 2024-04-30
Maintenance
Insert above this line
STATUSES
Not Started
In Progress
Blocked
Complete
SKIPPING
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))